## Sheet1
Sprint | User Story | Priority | Story Points
Sprint 1 | Analyze the current UI regression suite to identify redundant or outdated test cases | High | 3
Sprint 1 | Onboard new UI test cases for recent UI changes | High | 5
Sprint 1 | Validate the Health Check suite across existing environments | Medium | 3
Sprint 1 | Audit existing Postman API test cases for gaps in error condition coverage | High | 5
Sprint 2 | Remove obsolete UI test cases from the regression suite | High | 3
Sprint 2 | Enhance API test coverage with scenarios beyond happy path | High | 5
Sprint 2 | Integrate new API test cases into Newman + Jenkins pipeline | Medium | 3
Sprint 2 | Create checklist for common service failure scenarios in Health Check suite | Medium | 3
Sprint 3 | Identify dynamic APIs whose responses vary based on DB state | High | 5
Sprint 3 | Research DB query mechanisms to validate API responses | High | 5
Sprint 3 | Explore environment-specific configurations for Health Check suite | Medium | 3
Sprint 3 | Assess gaps in Extent report and UI Test result insights | Medium | 2
Sprint 4 | Develop POC to validate API data using DB queries | High | 5
Sprint 4 | Identify repeatable patterns to automate DB validation | Medium | 3
Sprint 4 | Evaluate performance testing tools (e.g., JMeter, k6) | Medium | 3
Sprint 4 | Define a minimal performance testing scenario for critical API | Medium | 3
Sprint 5 | Finalize DB integration for dynamic API validation and report results | High | 5
Sprint 5 | Create performance test scripts and collect baseline metrics | High | 5
Sprint 5 | Consolidate all test reports (UI, API, Health Check) for final review | Medium | 3
Sprint 5 | Document lessons learned, challenges, and future improvements | Medium | 2

## Sprint 1
# | User Story | Priority | Notes
1 | As an Automation Tester, I want to analyze the current UI regression suite to identify redundant or outdated test cases. | High | Maintenance focus
2 | As an Automation Tester, I want to onboard new UI test cases for recent UI changes, so regression is up-to-date. | High | Add new test coverage
3 | As an Automation Tester, I want to validate the Health Check suite across existing environments, to ensure stability. | Medium | Maintenance
4 | As an Automation Tester, I want to audit existing Postman API test cases for gaps in error condition coverage. | High | Prep for expansion in Sprint 2

## Sprint 2
# | User Story | Priority | Notes
5 | As an Automation Tester, I want to remove obsolete UI test cases from the regression suite. | High | Cleanup from Sprint 1
6 | As an Automation Tester, I want to enhance API test coverage with scenarios beyond happy path. | High | Negative & edge cases
7 | As an Automation Tester, I want to integrate new API test cases into Newman + Jenkins pipeline. | Medium | Ensure CI/CD visibility
8 | As an Automation Tester, I want to create a checklist for common service failure scenarios in Health Check suite. | Medium | Improve monitoring scope

## Sprint 3
# | User Story | Priority | Notes
9 | As an Automation Tester, I want to identify dynamic APIs whose responses vary based on DB state. | High | Kickstart DB integration plan
10 | As an Automation Tester, I want to research DB query mechanisms to validate API responses. | High | Focus on read-only verification
11 | As an Automation Tester, I want to explore environment-specific configurations for Health Check suite. | Medium | Make health checks portable
12 | As an Automation Tester, I want to assess gaps in Extent report and UI Test result insights. | Medium | Improve test observability

## Sprint 4
# | User Story | Priority | Notes
13 | As an Automation Tester, I want to develop POC to validate API data using DB queries. | High | From Sprint 3 research
14 | As an Automation Tester, I want to identify repeatable patterns to automate DB validation. | Medium | Prepare reusable components
15 | As an Automation Tester, I want to evaluate performance testing tools (e.g., JMeter, k6). | Medium | Exploration begins
16 | As an Automation Tester, I want to define a minimal performance testing scenario for critical API. | Medium | Define test scope

## Sprint 5
# | User Story | Priority | Notes
17 | As an Automation Tester, I want to finalize DB integration for dynamic API validation and report results. | High | Deliver working DB validations
18 | As an Automation Tester, I want to create performance test scripts and collect baseline metrics. | High | JMeter/k6 – critical endpoints
19 | As an Automation Tester, I want to consolidate all test reports (UI, API, Health Check) for final review. | Medium | Integration & reporting summary
20 | As an Automation Tester, I want to document lessons learned, challenges, and future improvements. | Medium | For retrospective & planning